## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 29 | C1715 | BETHANY ROAD AT MAYFIELD ROAD INTERSECTION IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This project involves intersection operational improvements incorporating a roundabout at the intersection of Bethany Road and Mayfield Road. The design of this project was awarded to Tetra Tech, Inc. in the amount of $127,670 by City Council on December 12, 2016. The conceptual design for this project was presented to City Council on June 5, 2017. As the acquisition of right of way progressed, it became necessary to revise the eastern leg of the roundabout. Change Order #1 was issued on April 2, 2018 which increased the design cost by $9,950 to $137,620. Final plans were delivered to the City on June 22, 2018. City Council awarded this project on November 5, 2018 to CMES. City Council also awarded the construction project management, inspection, and engineering to Atkins North America, Inc. Notice to proceed with construction was issued for July 24, 2019. Construction was delayed due to weather and utility relocations. Construction is complete and contractor has completed punchlist items related to sod and pavement markings. | CMES, Inc. | Tetra Tech, Inc. | June, 2018 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $2,258,335 | $2,256,294 | $2,041 | Green | Red | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-12 13:33:56
[17 empty] | SUM = 2,258,335 | SUM = 2,256,294 | SUM = 2,041