## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 31 | C1717 | OLD MILTON PARKWAY CAPACITY IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | This Project consists of widening Old Milton Parkway (SR 120) between GA 400 and State Bridge Road to provide a 6-lane divided section. The city is working with GDOT to expedite the project using mostly state and local funds. |  | AECOM | September, 2025 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $5,579,474 | $1,482,208 | $4,097,266 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2024-01-09 09:57:11
[17 empty] | SUM = 5,579,474 | SUM = 1,482,208 | SUM = 4,097,266