## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 32 | C1714 | BETHANY ROAD AT MID-BROADWELL ROAD INTERSECTION IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This project involves intersection operational improvements incorporating a roundabout at the intersection of Bethany Road and Mid Broadwell Road. The City has received numerous complaints regarding left turns onto Mid Broadwell Road from motorists traveling south on Bethany Road and from residents of Pindell Glen Subdivision trying to leave their subdivision. Residents have complained about the speed of vehicles on Mid Broadwell Road and have requested a reduction of the speed limit or the installation of a traffic signal or four-way stop. As these options do not meet warrants, a roundabout is proposed to reduce speeds in the area and assist in left-turn movements. The preliminary cost estimate for this project was $1.28 million with funding provided through T-SPLOST (transportation special purpose local option sales tax). The design of this project was awarded to Tetra Tech, Inc. in the amount of $131,170 by City Council on December 12, 2016. The conceptual design for this project was presented to City Council on June 5, 2017. | CMES, Inc. | Tetra Tech, Inc. | January, 2018 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,368,453 | $1,368,302 | $151 | Green | Red | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-12 13:54:18
[17 empty] | SUM = 1,368,453 | SUM = 1,368,302 | SUM = 151