## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 33 | C1713 | KIMBALL BRIDGE ROAD BICYCLE/PEDESTRIAN/OPERATIONAL IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Concept | This project involves pedestrian, bike, and operational improvements along Kimball Bridge Road between Westside Parkway and North Point Parkway connecting residential neighborhoods to Downtown Alpharetta, Avalon, schools, and parks. |  | AECOM |  |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,359,742 | $1,077,773 | $281,969 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2024-01-09 09:58:44
[17 empty] | SUM = 1,359,742 | SUM = 1,077,773 | SUM = 281,969