## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
JCR- 25 | JCR-020 | Medlock Bridge Road at State Bridge Improvements - Phase 1 | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Completed | This project will make improvements to the intersection of Medlock Bridge and State Bridge Road. Proposed improvements are adding a third southbound lane on SR 141/Medlock Bridge Road and a third eastbound and westbound lane on State Bridge Road. This will be accomplished using a combination of widening and restriping to minimize impacts. | Vertical Earth | WSP | June, 2020 | September, 2020 | July, 2021 | June, 2021 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Medlock-Bridge-Rd-at-State-Bridge-Rd | Sales Tax | $2,205,757 | $2,205,757 | $0 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2021 | 2022-08-22 15:03:34
[17 empty] | SUM = 2,205,757 | SUM = 2,205,757 | SUM = 0