## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
JCR- 28 | JCR-008 | Bell / Boles Corridor Operational & Safety Improvements - Bell Road at Rogers Circle (South) | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Completed | Project will introduce a roundabout at the intersection of Bell Road and Rogers Circle as well as a trail along Rogers Circle. | Ohmshiv | KCI | September, 2020 | December, 2020 | October, 2021 | September, 2021 | https://www.johnscreekga.gov/residents/public-works/tsplost/bell-and-boles-rd-corridor-operational-and-safety | Sales Tax | $2,026,935 | $2,026,935 | $0 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2021 | 2022-08-22 15:01:11
[17 empty] | SUM = 2,026,935 | SUM = 2,026,935 | SUM = 0