## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 34 | C1935 | WINDWARD PARKWAY WESTBOUND WIDENING - NORTH POINT PARKWAY TO GEORGIA 400 | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This is one of two projects which evolved from the conceptual design work comprising the "Windward Parkway Business District/Union Hill Road Capacity Improvements - TSPLOST Project". The project limits are from North Point Parkway to the northbound Georgia 400 on-ramp. Improvements will include: (1) The installation of a third travel lane from North Point Parkway to the northbound Georgia 400 on-ramp. All travel lanes will be 11'' wide. (2) The installation of a 4'' bike lane. (3) The installation of a 6'' wide sidewalk. (4) The lengthening of the existing dual left-turn lanes from westbound Windward Parkway to southbound North Point Parkway. The typical section will seek to match that of the "Windward Parkway Triple Left-Turn Lane at Georgia 400 Interchange" project. On Monday, May 6, 2019 design of the project was awarded to Tetra Tech, Inc. in the amount of $210,500.00. Bids were received on Thursday, May 14, 2020. The project was awarded to Sol Construction, LLC by City Council on Monday, June 15, 2020. | Sol Construction LLC | Tetra Tech, Inc. | February, 2020 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,302,037 | $1,182,286 | $119,751 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-11 14:52:06
[17 empty] | SUM = 1,302,037 | SUM = 1,182,286 | SUM = 119,751