## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 35 | C1934 | WINDWARD PARKWAY EASTBOUND WIDENING - WESTSIDE PARKWAY TO NORTH POINT PARKWAY | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Construction | This is one of two projects which evolved from the conceptual design work comprising the "Windward Parkway Business District/Union Hill Road Capacity Improvements - TSPLOST Project". The project limits are from Westside Parkway to North Point Parkway. Improvements will include: (1) The installation of a third travel lane from Westside Parkway to the southbound Georgia 400 on-ramp. All travel lanes will be 11'' wide. (2) The installation of a 4'' bike lane. (3) The installation of a 6'' wide sidewalk. The typical section will seek to match that of the "Windward Parkway Triple Left-Turn Lane at Georgia 400 Interchange" project. On Monday, May 6, 2019 design of the project was awarded to Tetra Tech, Inc. in the amount of $302,830.00. Design is complete. Bids were received on Thursday, May 14, 2020. Project was awarded to Sol Construction, LLC by City Council on Monday, June 15, 2020. The Notice to Proceed was issued August 8, 2020 and the project duration is anticipated to be 365 days. | Sol Construction LLC | Tetra Tech, Inc. | February, 2020 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,639,117 | $1,275,417 | $363,700 | Green | Yellow | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-12 12:56:26
[17 empty] | SUM = 1,639,117 | SUM = 1,275,417 | SUM = 363,700