## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 36 | C1933 | WEBB BRIDGE ROAD BIKE/PED/OPERATIONAL IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | This is one of two projects which evolved from the conceptual design work and community meetings comprising the "Academy Street/Webb Bridge Road: Bike/Ped/Operational Improvements - TSPLOST Project". The project limits are from the Big Creek Greenway crossing to Webb Bridge Way. Improvements include: (1) The installation of 8'' wide sidewalks along both sides of Webb Bridge Road. (2) The installation of 4'' bike lanes in both directions of travel along Webb Bridge Road. (3) A 3'' wide "beauty" strip will be provided on each side of Webb Bridge Road between the sidewalk and curb line. 5''x5'' tree wells/grates will be incorporated into this area and adjacent sidewalk. (4) The evaluation of a single-lane roundabout with slip lanes at the intersection with Southlake Drive / Park Bridge Park way. (5) The installation of a single-lane roundabout at the intersection with Webb Bridge Way. (6) The installation of pedestrian lighting along both sides of Webb Bridge Road and roadway lighting at the roundabouts. |  | Pond & Company | April, 2021 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $875,796 | $814,855 | $60,941 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:19:05
[17 empty] | SUM = 875,796 | SUM = 814,855 | SUM = 60,941