## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 37 | C1932 | ACADEMY STREET BIKE/PED/OPERATIONAL IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | This is one of two projects which evolved from the conceptual design work and community meetings comprising the "Academy Street/Webb Bridge Road: Bike/Ped/Operational Improvements - TSPLOST Project". The project limits are from Loxford Lane to Fire Station 81. Improvements will include: (1) The installation of a 6'' wide sidewalk with a 2'' grass strip along the north side of Academy Street to fill the gap between Alpharetta Presbyterian Church. The existing sidewalk along the south side will be maintained though limited portions may require reconstruction. (2) The installation of a 3'' striped shoulder to accommodate bicycles in both directions of travel from Loxford Lane to Wedgewood Drive. (3) The installation of left turn lanes between Loxford Lane and Wedgewood Drive where possible and the installation of landscaped medians between Loxford Lane and Wedgewood Drive where possible. The existing right-turn lanes at Dancliff Lane and Jamestown Trail will remain. |  | Pond & Company | August, 2020 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $289,575 | $275,490 | $14,085 | Green | Yellow | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:10:33
[17 empty] | SUM = 289,575 | SUM = 275,490 | SUM = 14,085