## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 22 | MIL-034 (Cogburn) | Cogburn Road Sidewalks | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Milton | Completed | Sidewalks, curb and drainage improvements along both sides of Cogburn Road from Bethany Bend to Oakstone Glen and Devonshire Farms | DAF Concrete | Wolverton | August, 2020 | January, 2019 | December, 2021 | November, 2021 | https://cleargov.com/georgia/fulton/city/milton/projects/1197/cogburn-road-sidewalks-_-tsplost | Sales Tax | $763,178 | $635,579 | $127,599 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:08:56
[17 empty] | SUM = 763,178 | SUM = 635,579 | SUM = 127,599