## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 38 | C1708 | GREENWAY EXTENSION TO FORSYTH COUNTY | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Alpharetta | Completed | This project involves the extension of the Big Creek Greenway north from Windward Parkway to connect to Forsyth County's greenway trail system. Completing this leg of the Big Creek Greenway will result in a trail system that runs more than 14 miles through Roswell, Alpharetta, and Forsyth County. Ultimately the trail system will span from the Chattahoochee River in Roswell to Bethelview Road in Forsyth County. | Integrated Construction and Nobility Inc | Pond & Company | April, 2019 | February, 2020 | June, 2021 | May, 2021 | https://alpharetta.projects.socrata.com/projects/C1708?stageId=Construction&tab=list | Sales Tax | $1,000,000 | $799,437 | $200,563 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2017 | 2021-10-13 13:13:19
[17 empty] | SUM = 1,000,000 | SUM = 799,437 | SUM = 200,563