## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 39 | C1638 | ACADEMY STREET/WEBB BRIDGE ROAD OPERATIONAL AND PEDESTRIAN/BICYCLE IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This is the parent project of the Academy Street Bike/Ped/Operational Improvements, Webb Bridge Road Bike/Ped/Operational Improvements and Webb Bridge Road (North Point Parkway to Greenway) projects. This project was for the conceptual layouts preparation for Academy Street and Webb Bridge Road from Alpharetta Presbyterian Church to Webb Bridge Way. |  | Pond & Company | January, 2019 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $451,828 | $451,828 | $0 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2023-02-17 19:36:37
[17 empty] | SUM = 451,828 | SUM = 451,828 | SUM = 0