## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 41 | C2104 | WEBB BRIDGE ROAD (NORTH POINT PARKWAY TO GREENWAY) | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Construction | This project will include the design of a new bridge over Big Creek to replace the existing vehicular and pedestrian bridges and of a 10'' wide multi-use trail with a 6'' wide planting strip along Webb Bridge Road from east of North Point Parkway to the Big Creek Greenway culvert under Webb Bridge Road. Street trees and pedestrian lighting will be provided along the shoulders. The design will seek to preserve the existing streetscape along the frontage of East Gate Subdivision. The new bridge will provide two 10.5'' travel lanes, header curb, 2'' separation (stamped concrete or concrete pavers) and a 10'' multi-use trail. Bike accommodations will be provided on the roadway from east of North Point Parkway to west of the proposed new bridge over Big Creek. At that point, bicyclists will be merged onto the multi-use trails. Refined concept plans and decision matrix were submitted on February 15, 2021. The design team was given direction to move forward with the "Alternate 3" concept based on this information. | Excellere Construction LLC | Pond & Company | February, 2022 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $692,508 | $382,143 | $310,365 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:20:05
[17 empty] | SUM = 692,508 | SUM = 382,143 | SUM = 310,365