## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 42 | C2054 | GA 400 BRIDGES | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Bidding | This project will add aesthetic elements to the bridges over GA 400 along Tradewinds Parkway, Kimball Bridge Road and Webb Bridge Road following the design of Encore Parkway. | [6 empty] | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $4,886,000 | $737,429 | $4,148,571 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:07:37
[17 empty] | SUM = 4,886,000 | SUM = 737,429 | SUM = 4,148,571