## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 43 | C2113 | ENCORE GREENWAY GATEWAY | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | The goal of the Encore Greenway Gateway project is to improve the connectivity (safety and simplicity) to the Big Creek Greenway from the intersection of Encore Parkway and North Point Parkway. Project will provide connectivity of the Big Creek Greenway to the west side of GA 400 and introduce a gateway feature to bring attention to the greenway. Project status meeting was held on January 10, 2022. AECOM is working on the construction plans and Design team is communicating with Recreation/Parks/Cultural Services and NFCID regarding the selection of railing, benches, garbage cans, bike racks, etc. A revised completion date of design will be examined once the City obtains access to the property and the design teams finishes all of the necessary soil borings. Design of the project is currently on-hold. |  | AECOM |  |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $628,096 | $155,569 | $472,527 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2026-05-04 15:23:46
[17 empty] | SUM = 628,096 | SUM = 155,569 | SUM = 472,527