## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MTP- 2 | Mountain Park | Pipe Lining Various Pipes under Public Roads | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Mountain Park | Design | Mountain Park desires to use the remaining portion of the first wave of TSPLOST toward the relining of storm pipes that cross under several significant roads within the City Limits. The pipes have already been inspected and identified and should be out to bid by Jan. 2022 | TBD | Integrated Science and Engineering | December, 2021 | January, 2022 | March, 2022 | February, 2022 |  | Sales Tax | $165,308 | $0 | $165,308 | Green | Green | Active | djohnson@intse.com | 2022 | 2021-09-30 13:20:10
[17 empty] | SUM = 165,308 | SUM = 0 | SUM = 165,308