## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 26 |  | Milo Fisher, Bay Street & Grant Street Pedestrian Improvements | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | Extend sidewalk on Milo Fisher to the intersection of Clayton Street, extend sidewalk on Bay Street to the intersection of Malone Street, install sidewalk on Grant street from Milo Fisher Street to Chestnut Street. | BOSS Concrete Construction, LLC |  | March, 2021 | April, 2021 | June, 2021 | May, 2021 |  | Sales Tax | $25,000 | $19,977 | $5,023 | Green | Green | Active | lthompson@fairburn.com | 2021 | 2021-09-09 11:55:01
[17 empty] | SUM = 25,000 | SUM = 19,977 | SUM = 5,023