## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 204 | QRP 1102 | Hunter Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Road Resurfacing- Hunter Rd | CW Matthews |  |  |  | August, 2019 |  |  | Sales Tax | $323,146 | $433,648 | $-110,502 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-10-12 19:57:45
[17 empty] | SUM = 323,146 | SUM = 433,648 | SUM = -110,502