## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
HA- 6 | HA-108 | Hapeville Paving Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Hapeville | Bidding | Paving of roads | TBD | Keck & Wood | August, 2021 | January, 2022 | April, 2022 | March, 2022 |  | Sales Tax | $600,000 | $1,360,567 | $-760,567 |  | Gray | Active | lsudduth@hapeville.org | 2021 | 2021-11-09 21:59:59
[17 empty] | SUM = 600,000 | SUM = 1,360,567 | SUM = -760,567