## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 51 | B 500 | Butner Road over Camp Creek | Tier 1 | Bridges | TSPLOST | City of South Fulton | Design | The proposed Butner Road over Camp Creek includes improvements to the bridge that will extend to the Camp Creek Parkway edge of pavement on the south leg of the intersection. A new bridge is proposed to replace the existing near the Butner Road/Camp Creek Parkway intersection. The proposed bridge will be wide enough to accommodate two traffic lanes of 24-ft wide, 30'' curb and gutter and 12-ft wide pedestrian sidewalk on the west side to tie into a proposed multi-use trail off the bridge and 6-ft wide sidewalk on the east side. A turning lane will be designed off the bridge to finish free flow and stacking length up to the intersection with Camp Creek Parkway. |  | William-Russell & Johnson | December, 2022 | April, 2020 | September, 2024 |  |  | Sales Tax | $1,600,000 | $61,911 | $1,538,089 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2023-03-05 00:19:21
[17 empty] | SUM = 1,600,000 | SUM = 61,911 | SUM = 1,538,089