## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 55 | OSI 601 | Butner Road @ Camp Creek Parkway | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The proposed Butner Road project is a capacity project that begins at the intersection of Camp Creek Parkway and extends approximately 1,000 feet to the north along Butner Road. It consists of widening the existing Butner Road by adding left and right-turn lanes, providing a nature trail at-grade crossing and updating the intersection signalization and guardrails, as a safety measure, on the east side of Butner Road to Merk Road. The travel lanes will be minimum 11 foot-wide with 2-foot stamped concrete and 12-foot trail on the east side. This project also includes signal upgrade and installation of new decorative mast arms. |  | American Engineers, Inc | December, 2022 | August, 2020 | January, 2025 |  |  | Sales Tax | $3,174,000 | $16,250 | $3,157,750 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:26:37
[17 empty] | SUM = 3,174,000 | SUM = 16,250 | SUM = 3,157,750