## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 56 | OSI 602 | Butner Road @ Union Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Intersection improvements will include the use of an oval roundabout or circular roundabout. A traffic report concluded that a roundabout is the best alternative to handle the traffic congestion at this intersection. Additional improvements include drainage, curb & gutter, street lights, and sidewalks. |  | American Engineers, Inc | December, 2022 | December, 2019 | August, 2024 |  | https://performance.fultoncountyga.gov/stories/s/v555-6sca | Sales Tax | $1,986,000 | $241,500 | $1,744,500 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:28:01
[17 empty] | SUM = 1,986,000 | SUM = 241,500 | SUM = 1,744,500