## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 58 | OSI 604 | Campbellton Road @ Stonewall Tell Road (Project Design on Hold) | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Construction | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. | CMC, INC | American Engineers, Inc | December, 2022 | April, 2020 | March, 2024 |  |  | Sales Tax | $1,422,000 | $172,932 | $1,249,068 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:40:45
[17 empty] | SUM = 1,422,000 | SUM = 172,932 | SUM = 1,249,068