## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 59 | OSI 605 | Campbellton-Fairburn Road @ Jones Road (Project Design on Hold) | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Geometric and capacity improvements to include traditional or roundabouts |  | American Engineers, Inc | August, 2018 |  | August, 2019 |  |  | Sales Tax | $1,464,000 | $0 | $1,464,000 | Green | Green | Active | roussan.francois@fultoncountyga.gov |  | 2021-05-03 22:55:24
[17 empty] | SUM = 1,464,000 | SUM = 0 | SUM = 1,464,000