## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 62 | OSI 608 | Enon Road @ Stonewall Tell Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | .Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  | AEI | May, 2023 | December, 2020 | October, 2024 |  |  | Sales Tax | $1,674,000 | $104,310 | $1,569,690 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-05 00:40:33
[17 empty] | SUM = 1,674,000 | SUM = 104,310 | SUM = 1,569,690