## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 66 | OSI 613 | Old Fairburn Road @ Union Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5' wide sidewalks. Due to the proximity, this project will be delivered as a single construction project along with OSI 615 Stonewall Tell Road @ Union Road. |  | American Engineers, Inc | March, 2023 | December, 2020 | July, 2025 |  |  | Sales Tax | $1,464,000 | $38,399 | $1,425,601 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:46:59
[17 empty] | SUM = 1,464,000 | SUM = 38,399 | SUM = 1,425,601