## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 67 | OSI 614 | Rivertown Road @ Cedar Grove Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Bidding | Improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5' wide sidewalks. |  | American Engineers, Inc | February, 2023 | July, 2024 | March, 2023 |  | https://performance.fultoncountyga.gov/stories/s/f85b-5vnc | Sales Tax | $1,310,000 | $98,319 | $1,211,681 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:49:10
[17 empty] | SUM = 1,310,000 | SUM = 98,319 | SUM = 1,211,681