## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 68 | OSI 615 | Stonewall Tell Road @ Union Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5Æ wide sidewalks. Due to the proximity, this project will be delivered as a single construction project along with OSI 613 Old Fairburn Road at Union Road. |  | American Engineers, Inc | March, 2023 | December, 2020 | July, 2025 |  | https://performance.fultoncountyga.gov/stories/s/itui-hn3h | Sales Tax | $1,488,000 | $32,049 | $1,455,951 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-06 12:28:39
[17 empty] | SUM = 1,488,000 | SUM = 32,049 | SUM = 1,455,951