## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 71 | OSI 618 | Welcome All Road @ Scarboro Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will address safety improvements, congestion mitigation, and geometric design standards. |  | AEI | May, 2023 | May, 2021 | December, 2024 |  |  | Sales Tax | $1,556,400 | $84,643 | $1,471,757 | Green | Green | Active | roussan.francois@fultoncountyga.gov |  | 2023-03-06 12:37:09
[17 empty] | SUM = 1,556,400 | SUM = 84,643 | SUM = 1,471,757