## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 92 | PBI 900 | Danforth Road (Rehoboth Circle to Cascade Road) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Construction | The project scope includes the installation of 5 foot-wide concrete ADA (Americans with Disabilities Act) compliant sidewalks, concrete curb and gutter, a 2- foot stamped concrete, drainage and pedestrian lighting on both sides of Danforth Road from Rehoboth Circle to Cascade Road. The approximate length of the project is 0.8 mile. | CMC, INC | AEI | September, 2022 | February, 2022 | December, 2023 |  |  | Sales Tax | $2,250,000 | $90,653 | $2,159,347 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-06 12:44:33
[17 empty] | SUM = 2,250,000 | SUM = 90,653 | SUM = 2,159,347