## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 93 | PBI 901 | Enon Road (Lynarbor Lane to Sanford J. Jones) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Design | Proposed project includes sidewalk facilities along both sides of Enon Road from just north of Lynarbor Lane and extends to Sanford J. Jones Boulevard for a distance of approximately 1.5 miles. Project features include adding 5-6 foot sidewalks along the west side, 8-ft. sidewalks along east side from Lynarbor Lane to Sanford J. Jones Boulevard. Drainage improvements, curb and gutter, and 2-foot stamped concrete is also included. |  | AAEI | March, 2023 | September, 2020 | June, 2024 |  |  | Sales Tax | $2,000,000 | $43,650 | $1,956,350 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-06 12:46:48
[17 empty] | SUM = 2,000,000 | SUM = 43,650 | SUM = 1,956,350